## Sprint Backlog
Sprint Backlog
Task ID | Task | Description | Story ID | Backlog ID | Sprint# | State | Estimate Time (Hours) | Assign to | Note
T01 | Phân tích mô hình chức năng |  |  |  | 1 | New | 7 | Trường
T02 | Phân tích và thiết kế database, ERDiagram |  |  |  | 1 | New | 7 | Trường
Quản lý tài khoản
T03 | Draw: Usecase tài khoản |  |  | PB01 | 1 | New | 7 | Công
T04 | Code: Giao diện đăng nhập |  |  |  | 1 | New | 7 | Công
T05 | Code: Chức năng đăng nhập |  | RQ01 |  | 1 | New | 7 | Đức, Trường
T06 | Code: Hiển thị danh sách quản lý tài khoản |  | RQ02 |  | 1 | New | 7 | Đức, Trường
T07 | Code: Chức năng thêm tài khoản mới |  | RQ03 |  | 1 | New | 7 | Đức, Trường
T08 | Code: Chức năng cập nhật tài khoản |  |  |  | 1 | New | 7 | Đức, Trường
T09 | Code: Chức năng xóa tài khoản |  |  |  | 1 | New | 7 | Đức, Trường
T10 | Test: Unit Test |  |  |  | 1 | New | 8 | Hào
T11 | Test: Integration Test |  |  |  | 1 | New | 8 | Hào
Quản lý sản phẩm
T12 | Draw: Usecase sản phẩm |  |  | PB02 | 2 | New | 8 | Công
T13 | Code: Hiển thị danh sách quản lý sản phẩm |  | RQ05 |  | 2 | New | 8 | Đức, Hào
T14 | Code: Chức năng thêm sản phẩm mới |  | RQ06 |  | 2 | New | 8 | Đức, Hào
T15 | Code: Chức năng cập nhật sản phẩm |  |  |  | 2 | New | 8 | Đức, Hào
T16 | Code: Chức năng xóa sản phẩm |  |  |  | 2 | New | 8 | Đức, Hào
T17 | Code: Giao diện mua hàng |  |  |  | 2 | New | 8 | Công
T18 | Code: Hiển thị sản phẩm ở trang mua hàng |  | RQ07 |  | 2 | New | 8 | Đức, Hào
T19 | Test: Unit Test |  |  |  | 2 | New | 12 | Hào
T20 | Test: Integration Test |  |  |  | 2 | New | 12 | Hào
Giỏ hàng
T21 | Draw: Usecase giỏ hàng |  |  | PB03 | 3 | New | 8 | Công
T22 | Code: Giao diện giỏ hàng |  |  |  | 3 | New | 8 | Công
T23 | Code: Chức năng thêm sản phẩm vào giỏ hàng |  |  |  | 3 | New | 8 | Đức, Công
T24 | Code: Hiển thị danh sách sản phẩm đã thêm vào giỏ hàng |  | RQ08 |  | 3 | New | 8 | Đức, Công
T25 | Code: Chức năng xóa sản phẩm trong giỏ hàng |  |  |  | 3 | New | 8 | Đức, Công
T26 | Code: Chức năng thanh toán giỏ hàng |  | RQ09 |  | 3 | New | 8 | Đức, Công
T27 | Code: Chức năng gửi mail cho KH hóa đơn vừa thanh toán |  |  |  | 3 | New | 8 | Đức, Công
T28 | Test: Unit Test |  |  |  | 3 | New | 12 | Hào
T29 | Test: Integration Test |  |  |  | 3 | New | 12 | Hào

## Release Backlog
Backlog ID | Backlog | STORY / FEATURE / REQUEST |  |  | Story ID | Priority | Business Value | Sprint# | State | Note
|  | As a/an [User role] | I want to [Goal] | So that [reason]
PB01 | Quản lý tài khoản | Admin | Trang web của tôi phải đăng nhập mới sử dụng được các chức năng quản lí | Tôi có thể bảo mật thông tin của trang web | RQ01 | 1 | High | 1 | New
|  | Admin | Danh sách quản lý tài khoản truy cập vào trang web | Tôi có thể biết có bao nhiêu tài khoản tồn tại | RQ02 | 2 | Medium | 1 | New
|  | Admin | Thêm, xóa, sửa tài khoản trên trang web | Tôi có thể quản lí thông tin tài khoản trên trang web của mình | RQ03 | 2 | High | 1 | New
PB02 | Quản lý sản phẩm | Admin | Danh sách quản lý sản phẩm | Tôi có thể biết có bao nhiêu mặt hàng đang tồn tại trên trang web | RQ05 | 3 | Medium | 2 | New
|  | Admin | Thêm, xóa, sửa sản phẩm trên trang web | Tôi có thể quản lí sản phẩm tài khoản trên trang web của mình | RQ06 | 3 | High | 2 | New
|  | User | Trang mua hàng hiển thị tất cả các mặt hàng trong danh sách quản lí quản phẩm | Tôi có thể cho khách hàng xem các sản phẩm kinh doanh của trang web | RQ07 | 4 | Medium | 2 | New
PB03 | Giỏ hàng | User | Trang giỏ hàng để lưu trữ sản phẩm khách hàng muốn mua hoặc xóa sản phẩm khách hàng không muốn mua | Tôi có thể cho khách hàng dễ dàng mua lựa chọn các mặt hàng trên trang web | RQ08 | 4 | High | 3 | New
|  | User | Trang thanh toán giỏ hàng gồm các sản phẩm và thông tin liên lạc của khách hàng | Tôi có thể liên lạc cho khách hàng và giao hàng tận nơi | RQ09 | 4 | Medium | 3 | New

## Product Backlog
ID | STORY / FEATURE / REQUEST |  |  | Priority | Business Value | Acceptance Criteria | State | Note
| As a/an [User role] | I want to [Goal] | So that [reason]
RQ01 | Admin | Trang web của tôi phải đăng nhập mới sử dụng được các chức năng quản lí | Tôi có thể bảo mật thông tin của trang web | 1 | High |  | New
RQ02 | Admin | Danh sách quản lý tài khoản truy cập vào trang web | Tôi có thể biết có bao nhiêu tài khoản tồn tại | 2 | Medium |  | New
RQ03 | Admin | Thêm mới, cập nhật hoặc xóa tài khoản trên trang web | Tôi có thể quản lí thông tin tài khoản trên trang web của mình | 2 | High |  | New
RQ04 | User | Trang chủ giới thiệu sản phẩm về các mặt hàng kinh doanh của trang web | Tôi có thể cho khách hàng biết xuất xứ, nguồn gốc, kiểm định, sự an toàn của sản phẩm chúng tôi | 1 | Low |  | New
RQ05 | Admin | Danh sách quản lý sản phẩm | Tôi có thể biết có bao nhiêu mặt hàng đang tồn tại trên trang web | 3 | Medium |  | New
RQ06 | Admin | Thêm mới, cập nhật hoặc xóa sản phẩm trên trang web | Tôi có thể quản lí sản phẩm tài khoản trên trang web của mình | 3 | High |  | New
RQ07 | User | Trang mua hàng hiển thị tất cả các mặt hàng trong danh sách quản lí quản phẩm | Tôi có thể cho khách hàng xem các sản phẩm kinh doanh của trang web | 4 | Medium |  | New
RQ08 | User | Trang giỏ hàng để lưu trữ sản phẩm khách hàng muốn mua hoặc xóa sản phẩm khách hàng không muốn mua | Tôi có thể cho khách hàng dễ dàng mua lựa chọn các mặt hàng trên trang web | 4 | High |  | New
RQ09 | User | Trang thanh toán giỏ hàng gồm các sản phẩm và thông tin liên lạc của khách hàng | Tôi có thể liên lạc cho khách hàng và giao hàng tận nơi | 4 | Medium |  | New

## RULE
Title: Brief description of the PBI. The title of a PBI should represent the intent of the PBI.
Iteration: Indicate the sprint in which a PBI is implemented. When you first enter a PBI into TFS, iteration defaults to the current project, meaning that it's not yet scheduled for a sprint. During the sprint planning meeting, when the team commits to implementing a PBI, you set this field to the iteration representing the sprint.
Assigned To: Indicates the owner of a PBI. The product owner who's assigned to the PBI is responsible for answering questions and providing details about the PBI. This person is also responsible for verifying that the PBI meets acceptance criteria before the team finishes the sprint. When a PBI is first created, the Assigned To field defaults to the user entering the PBI, so it's best to set it to the product owner at that point.
State: Use the State field to track the current state of a PBI.
New: The PBI is entered into TFS. It may be just the initial text of a user story, or it may be fully defined with test cases and acceptance criteria.
Approved: The PBI has been approved by the product owner and is a candidate to be assigned to a sprint at the sprint planning meeting.
Committed: The PBI has been assigned to a sprint, and the team has committed to completing it.
Removed: The PBI is no longer needed. This is useful when you're pruning the backlog to remove duplicates, to consolidate similar PBIs, or to simply remove the PBIs that are such low priority that they will never be built.
Done: The PBI is complete, and the product owner has tested and verified it.
Reason: Reason is a read - only field that is predefined based on the state and transition of the PBI.
New
New Backlog Item : The PBI was just entered but not yet prioritized or estimated.
Reconsidering Backlog Item : The item had been removed but was reconsidered and is now back in the backlog.
Approved
Approved by the Product Owner : The PBI was approved by the product owner and is now ready to be included in a sprint.
Work Stopped : The PBI had been committed to a sprint, but the team decided to stop work on it and put it back in the backlog for future sprint.
Committed : Commitment Made by the Team : The team has committed to implement the PBI in a sprint.
Additional Work Found: The PBI was previously considered done, but more work was found, so it's back in the backlog.
Removed: The PBI was removed from the backlog.
Done: The work on the PBI is finished.
Backlog Priority: Used to determine the position of the PBI on the product backlog. New PBIs default to a backlog priority of 1,000. This field represents an item's location in the backlog, not its business value. It indicates when the PBI should be scheduled, relative to other items on the list.
Effort: Used to track the estimated effort required to implement a PBI, relative to other PBIs in the release. Relative is the operative word here, as the effort is not in terms of hours or days. Rather, it's a just a number used to compare the relative effort required for PBIs.
Business Value: Used to track the amount of business value delivered by a PBI. You should choose a number between 1 and 100 to represent the amount of business value that implementing the PBI will deliver to your customers. Higher numbers imply greater business value. A PBI with a low business value and a high effort estimate probably won't get scheduled into a sprint and will remain on the product backlog.
Description: Used to provide a detailed description of a PBI. This is where the product owner describes what the feature does and who needs it. If you're defining PBIs via user stories, then this is the written record of the feature.
Acceptance Criteria: Used to provide a bulleted list of criteria a PBI must meet before it will be accepted as done. The product owner defines the acceptance criteria either when initially creating the PBI or when the PBI is added to a sprint. It's critical to have sufficient information in this field for a PBI because these are the criteria against which the team will build the feature during the sprint.
Conclusion
In this article, we have seen that the product backlog is the list of requirements for the system. It is the central focus of a Scrum team, representing the features that the team will build into the product. The product owner defines and prioritizes the PBIs. Each PBI stores the details of one product feature. It describes its business benefit, test cases, and acceptance criteria.